## Project Timeline
Phase | Milestone | Owner | Target Date | Status | Dependencies | Notes
Phase 1: Board Approval | Complete current 340B revenue analysis | CFO + Pharmacy | Month 1 Week 1 | Not Started | Contract pharmacy data access | Pull from contract pharmacy reports
| Entity-owned feasibility model (3-year ROI) | CFO | Month 1 Week 2 | Not Started | Revenue analysis complete | Include rebate model cash flow
| Board presentation and approval vote | CEO + CFO | Month 1 Week 4 | Not Started | Feasibility model complete | Lead with revenue gap analysis
| Hire Pharmacist-in-Charge (PIC) | HR + Pharmacy | Month 1-2 | Not Started | Board approval | CA BPC requires PIC for license
Phase 2: Licensing | Submit CA Board of Pharmacy application (17A-66) | PIC + Legal | Month 1 Week 4 | Not Started | PIC hired, space identified | 60-120 day processing time
| Submit DEA Form 224 registration | PIC | Month 2 Week 1 | Not Started | Board of Pharmacy app filed | 4-6 week processing
| Submit HRSA Change in Scope (if new address) | Grants Manager | Month 1 Week 4 | Not Started | Board approval | 60-90 days — submit early!
| Register pharmacy in 340B OPAIS | PIC + Compliance | Month 2 Week 2 | Not Started | HRSA CIS approved (if needed) | Links pharmacy to covered entity
| Establish wholesale distributor accounts | PIC + Finance | Month 2 Week 3 | Not Started | 340B OPAIS active | McKesson/Cardinal/Amerisource
| Physical pharmacy buildout complete | Facilities + PIC | Month 2 Week 4 | Not Started | Board approval, space leased | Must pass BOP inspection
| Board of Pharmacy inspection passed | PIC | Month 3 | Not Started | Buildout complete, app filed | Schedule when build is 90% done
Phase 3: Technology | Select and contract 340B split-billing software | IT + Pharmacy + Compliance | Month 2 Week 1 | Not Started | Board approval | Sentry/MacroHelix/Verity
| EHR integration with 340B software | IT + EHR Vendor | Month 2-3 | Not Started | Software selected | Critical for auto-eligibility
| EHR prescription routing configured (default internal) | IT + Clinical | Month 3 Week 1 | Not Started | EHR integration live | Default to on-site pharmacy
| 340B eligibility screening in EHR check-in workflow | IT + Clinical Ops | Month 3 Week 2 | Not Started | EHR integration live | Automatic, not manual
Phase 4: Launch | Soft launch — fill prescriptions for established patients | PIC + Clinical | Month 3 | Not Started | All licenses in hand | Start with top 50 medications
| Train 100% of prescribers on 340B workflows | Clinical Director + PIC | Month 3 Week 2 | Not Started | EHR configured | In-person training required
| Train front desk + MAs on pharmacy routing scripts | Clinical Ops | Month 3 Week 2 | Not Started | EHR configured | "Fill your Rx before you leave"
| First capture rate audit | Pharmacy Manager | Month 4 Week 1 | Not Started | 2+ weeks of dispensing data | Target: 60%+ initial
Phase 5: Optimization | Expand pharmacy hours (evenings/weekends) | PIC + HR | Month 4 | Not Started | Steady operations established | Hire additional tech if needed
| Launch medication delivery service | PIC + Operations | Month 5 | Not Started | Volume justifies delivery cost | Homebound + rural patients
| Formulary optimization (top 200 Rx analysis) | Clinical Pharmacist | Month 4-5 | Not Started | 3+ months dispensing data | Prioritize high-margin generics
| Capture rate reaches 85%+ | Pharmacy Manager | Month 6 | Not Started | All optimization levers active | Weekly audit of leaked Rx
| Net 340B savings reaches $40K+/month | CFO + PIC | Month 6 | Not Started | 85%+ capture rate | Track against feasibility model
Ongoing: Compliance | Monthly self-audit (25 random Rx) | Compliance Officer | Monthly | Not Started | Dispensing data available | Document findings + corrective actions
| Quarterly compliance reconciliation | Compliance + Finance | Quarterly | Not Started | 3+ months data | 340B database vs. EHR encounters
| Annual external 340B audit | External Consultant | Annually | Not Started | Budget $10-20K | Before HRSA audit cycle
| Rebate model cash flow monitoring | CFO | Monthly | Not Started | Rebate pilot drugs on formulary | Track 45-day reimbursement lag

## Capital Budget
Category | Item | Low Estimate | High Estimate | Your Budget | Notes
Licensing & Registration
| CA Board of Pharmacy license | 600 | 600 |  | Application + inspection
| DEA registration | 888 | 888 |  | Biennial fee
| Legal counsel (pharmacy setup) | 5000 | 10000 |  | Operating agreements, DEA, contracts
| Pharmacy consultant | 8000 | 15000 |  | Compliance framework design
| SUBTOTAL: Licensing | 6488 | 11488 | 0
Physical Buildout
| Dispensing area construction/renovation | 30000 | 120000 |  | Depends on existing space
| Medication storage (refrigeration, safes, shelving) | 8000 | 25000 |  | Controlled substance safes required
| POS and inventory hardware | 5000 | 15000 |  | Barcode scanners, terminals
| Security systems | 3000 | 10000 |  | Board of Pharmacy requirement
| ADA compliance modifications | 46000 | 170000 | 0 | Patient consultation area
SUBTOTAL: Buildout
Technology
| 340B split-billing software (Year 1) | 15000 | 60000 |  | Sentry/MacroHelix/Verity
| Pharmacy management system | 5000 | 15000 |  | Must integrate with EHR
| EHR integration setup | 5000 | 10000 |  | One-time configuration
| ePrescribing connectivity | 2000 | 5000 |  | Surescripts enrollment
| Automated dispensing equipment | 27000 | 90000 | 0 | Optional — improves throughput
SUBTOTAL: Technology
Annual Staffing
| Pharmacist-in-Charge | 140000 | 180000 |  | Required by CA law
| Pharmacy Technician (1-2) | 45000 | 130000 |  | $45-65K each
| Clinical Pharmacist (MTM) | 130000 | 160000 |  | Medication therapy management
| Administrative support | 315000 | 470000 | 0 | Prior auth, insurance verification
SUBTOTAL: Staffing
TOTAL YEAR 1 INVESTMENT |  | 394488 | 741488 | 0 | All categories combined

## Cash Flow Model
340B Pharmacy Cash Flow Model — 12-Month Projection
ASSUMPTIONS (edit blue cells)
Monthly eligible prescriptions (steady state) | 2000 | Total Rx volume when fully operational
Capture rate Month 3 | 40% | Initial capture rate at soft launch
Capture rate Month 6 | 70% | Mid-optimization capture rate
Capture rate Month 9+ | 85% | Target steady-state capture rate
Average 340B spread per Rx (margin) | 25 | Reimbursement minus 340B ceiling price
Monthly pharmacy operating cost | 30000 | Staff + supplies + overhead
Rebate pilot % of volume | 10% | % of Rx affected by rebate pilot
Rebate reimbursement delay (days) | 45 | Cash flow lag for rebate pilot drugs
Metric | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Year 1 Total
Capture Rate | 0% | 0% | 40% | 55% | 63% | 70% | 75% | 78% | 85% | 85% | 85% | 85%
Rx Captured (340B) | 0 | 0 | 800 | 1100 | 1260 | 1400 | 1500 | 1560 | 1700 | 1700 | 1700 | 1700 | 14420
Gross 340B Savings | 0 | 0 | 20000 | 27500 | 31500 | 35000 | 37500 | 39000 | 42500 | 42500 | 42500 | 42500 | 360500
Operating Costs | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 300000
NET 340B Savings | 0 | 0 | -10000 | -2500 | 1500 | 5000 | 7500 | 9000 | 12500 | 12500 | 12500 | 12500 | 60500
Rebate Pilot Impact | 0 | 0 | 2000 | 2750 | 3150 | 3500 | 3750 | 3900 | 4250 | 4250 | 4250 | 4250 | 36050
Working Capital Tied Up | 0 | 0 | 3000 | 4125 | 4725 | 5250 | 5625 | 5850 | 6375 | 6375 | 6375 | 6375
Cumulative Net Savings | 0 | 0 | -10000 | -12500 | -11000 | -6000 | 1500 | 10500 | 23000 | 35500 | 48000 | 60500 | 60500

## Compliance Checklist
Audit Area | Requirement | Frequency | Owner | Status | Last Completed | Findings/Notes
Patient Eligibility | Random sample audit: 25 Rx have qualifying encounters | Monthly | Compliance Officer | Not Started |  | Document every audit
| Encounter recency check: all 340B patients seen within 12 months | Monthly | Pharmacy Manager | Not Started |  | Flag patients approaching threshold
| Provider-patient relationship documented (not just lab/referral) | Monthly | Compliance Officer | Not Started |  | Must be face-to-face encounter
Duplicate Discount | Split-billing software correctly identifies Medi-Cal patients | Monthly | IT + Pharmacy | Not Started |  | Reconcile with Medi-Cal claims
| No 340B pricing on Medicaid-rebate-eligible drugs | Monthly | Pharmacy Manager | Not Started |  | Zero tolerance for dual discount
| Quarterly reconciliation: 340B dispensing vs. Medi-Cal claims | Quarterly | Finance + Compliance | Not Started |  | Required before external audit
Diversion Prevention | 340B drugs dispensed only to covered entity patients | Monthly | Pharmacy Manager | Not Started |  | Software should auto-block
| No walk-in 340B dispensing to non-patients | Ongoing | Pharmacy Staff | Not Started |  | Training required
| Child/subsidiary sites properly registered in OPAIS | Annually | Grants Manager | Not Started |  | Check after any scope changes
Audit Trail | Complete chain: encounter → Rx → eligibility → dispense → reimburse | Monthly | Compliance Officer | Not Started |  | HRSA reviews this chain
| 340B database backed up and accessible | Weekly | IT | Not Started |  | Must survive hardware failure
| Audit binder updated with monthly findings + corrective actions | Monthly | Compliance Officer | Not Started |  | Hand to HRSA when they arrive
Program Registration | 340B OPAIS registration current and accurate | Annually | Grants Manager | Not Started |  | Verify after any org changes
| HRSA grant active and in good standing | Annually | Grants Manager | Not Started |  | Grant lapse = 340B exclusion
| All pharmacy locations on HRSA scope of project | Annually | Grants Manager | Not Started |  | Submit CIS for new locations
External Audit | Annual external 340B compliance audit | Annually | CFO + Compliance | Not Started |  | Budget $10-20K; do before HRSA
Rebate Model | 45-day rebate claims submitted on time | Monthly | Pharmacy Manager | Not Started |  | For pilot drugs only
| Working capital reserve adequate for rebate cash flow gap | Monthly | CFO | Not Started |  | 2 months of pilot drug wholesale

## OKR Tracker
340B Pharmacy Launch — OKR Tracker
Objective: Launch entity-owned 340B pharmacy generating $40K+/month in net savings within 6 months
Key Result | Owner | Metric | Baseline | Target | Current | % Progress | Status
Board of Pharmacy license + HRSA OPA registration complete | PIC + Legal | License status | Not started | Both complete by Month 2 |  |  | Not Started
Achieve 85% 340B capture rate on eligible Rx | Pharmacy Mgr + Clinical Ops | Capture rate % |  | 85% |  |  | Not Started
Train 100% of prescribers on 340B EHR workflows | Clinical Dir + IT | Training completion % | 0% | 100% by Month 2 |  |  | Not Started
Generate ≥$40K/month net 340B savings | CFO + PIC | Monthly net savings | $0 | $40,000+ by Month 6 |  |  | Not Started
100% audit trail for every dispensed Rx | Pharmacy Mgr + Compliance | Monthly audit pass rate | N/A | 100% |  |  | Not Started
Rebate model cash flow reserve established | CFO | Reserve balance | $0 | 2 months wholesale cost |  |  | Not Started
External 340B audit completed (Year 1) | CFO + Compliance | Audit status | Not scheduled | Complete by Month 12 |  |  | Not Started
Formulary covers 90%+ of top 200 Rx | Clinical Pharmacist | Formulary coverage % |  | 90%+ |  |  | Not Started